## Capital works
Project | Responsible officer | Authority (USD) | Outlay to date (USD) | Location | Kick-off | Contract
Project Saltmarsh | Ottilie Farquhar | 460000 | 187946.5 | Whitby | 2026-04-13 | WHB-0418-26
Project Weirgate | Bastian Greenhalgh | 125000 | 98340.75 | Falmouth | 2026-06-01 | WHB-0562-26

## Harbour services
Project | Envelope (USD) | Owner | Depot | Actual spend (USD) | Order ref | Start date
Scheme Fallowbeck | 238500 | Leonie Radcliffe | Grimsby | 229871.4 | WHB-0691-26 | 2026-05-18
Pilot Lodestar | 58000 | Caspar Wetherby | Harwich | 63512.8 | WHB-0837-26 | 2026-07-27

## Risk register
Project | Severity | Risk | Raised by | Date
Project Saltmarsh | Low | Dredging consent delayed; 272,053.50 USD of the allocation is undrawn | Ottilie Farquhar | 2026-08-19
Project Weirgate | High | Berthing revenue fell seven percent after the Grimsby quay closure | Bastian Greenhalgh | 2026-08-27
Scheme Fallowbeck | Medium | Tarrant Marine Supplies delivered 164 units short of the August commitment | Leonie Radcliffe | 2026-09-02
Pilot Lodestar | High | Spend exceeds allocation by 5,512.80 USD | Caspar Wetherby | 2026-09-10